## Sheet1
|  | Dur. | Earliest | Earliest | Latest | Latest | Total
Tasks | Assign | Estim. | Start | Finish | Start | Finish | Slack
(Main) Main GUI | Tyler & Kyle | 9hrs | 0 | 9 | N/A | N/A | 0
(Main) Scheduler Config Editor | Tyler | 4hrs | 9 | 13 | N/A | N/A | 0
(Sub-T) Faculty Management | Damion | 2hrs | 13 | 15 | N/A | N/A | 0
(Sub-T) Course Management | Shane | 6hrs | 15 | 21 | N/A | N/A | 0
(Sub-T) Room Management | Chayse | 8hrs | 21 | 29 | N/A | N/A | 0
(Sub-T) Lab Management | Mohamed | 7hrs | 29 | 36 | N/A | N/A | 0
(Sub-T) Config Management | Kyle | 4hrs | 36 | 40 | N/A | N/A | 0
(Main) Schedule Generator | Tyler & Kyle | 6hrs | 40 | 46 | N/A | N/A | 0
(Main) Schedule Viewer | Shane | 12hrs | 46 | 58 | N/A | N/A | 0
(Sub-T) Navig btw gen sch | Chayse | 3hrs | 58 | 61 | N/A | N/A | 0
(Sub-T) Tabular output | Tyler & Kyle | 14hrs | 61 | 75 | N/A | N/A | 0
(Sub-T) Export Sch Action | Shane | 6hrs | 75 | 81 | N/A | N/A | 0
(Sub-T) Import Sch Action | Shane | 6hrs | 81 | 87 | N/A | N/A | 0