## Sheet1
|  | Dur. | Earliest | Earliest | Latest | Latest | Total
Activity | Respon | Estim. | Start | Finish | Start | Finish | Slack
Faculty Management | Damion | 4hrs | 0 | 4 | 0 | 4 | 0
Course Management | Shane | 5hrs | 4 | 9 | 4 | 9 | 0
Room Management | Chayse | 3hrs | 9 | 12 | 9 | 12 | 0
Lab Management | Mohamed | 5hrs | 12 | 17 | 12 | 17 | 0
Config Management | Kyle | 10hrs | 17 | 27 | 17 | 27 | 0
Run the scheduler | Tyler | 4hrs | 27 | 31 | 27 | 31 | 0
Display the schedules | Tyler | 3hrs | 31 | 34 | 31 | 34 | 0
Test the modification to the configuration file | Kyle | 5hrs | 34 | 39 | 34 | 39 | 0